0.1 E     Seed System Security Assessment (SSSA)  OVERALL WORK SCHEDULE-

| DAY | Date | Work content | Comments |
| --- | --- | --- | --- |
| 1 | Monday |  | Opening meeting; two-day introduction and training | Day 1 am: welcome, overview presentations- why SSSA, speeches Day 1-pm-methods discussion Day 2- methods Field logistics |
| 2 | Tuesday |  |  |  |
| 3 | Wednesday |  | Site 1 assessment training+ all teams together | Each site normally takes 5 days. However, because this is a general training and many people will be involved—the work can be completed in 4 days Data entry for individual questionnaires should start at this site. (so entry should be on-going) |
| 4 | Thursday, |  |  |  |
| 5 | Friday |  |  |  |
| 6 | Saturday |  |  |  |
| 7 | Sunday |  | Travel to another site. One full team at each site. |  |
| 8 | Monday |  | Sites 2, 3, and 4 simultaneous different site assessments | Each site normally takes 5 days Data entry for individual questionnaires should start at this site. (so entry should be on-going) |
| 9 | Tuesday |  |  |  |
| 10 | Wednesday |  |  |  |
| 11 | Thursday |  |  |  |
| 12 | Friday |  |  |  |
| 13 | Saturday |  | All return central place—for debriefing |  |
| 14 | Sunday |  | Rest day | Some work on data analysis |
| 15 | Monday |  | Data finalization Formulation of concrete recommendations | Data analysis + summary + Development of workplans for short and medium term |
| 16 | Tuesday |  | “ | “ |
| 17 | Wednesday |  | Report writing for a few team members | “ |
| 18 | Thursday |  | Preparation of public presentation | “ |
| 19 | Friday |  | PUBLIC FEEDBACK SESSION | Key is to get donors, Senior Stakeholders at feedback |